## Sheet1
S.No | Tasks | Type of task | No of people required | Person | Progress | Completion Date
1 | Exploring yelp dataset - find which all features, regions exist | Data exploration | 2 |  | Done | 2018-10-06
2 | Isolate LA data from yelp data - coding | Data preprocessing | 1 | Devershi | Working
3 | For LA yelp data, Find how much missing data exist - which restaurants have all data missing, some data missing - separate missing data vs clean data | Data preprocessing | 1 | Devershi | Working
4 | Yelp business json processing |  | 1 | Rimsha | Working
5 | Crawling to get inspection/voilations |  | 2 | Rajdeep/Ajay | Working
6 | Based on task 1, Pick up regions and find government provided data availability online, if they have health score, format of data (csv, excel, to be scraped?) | Data collection | 2 |  | Done | 2018-10-06
7 | Study existing papers on finding health score for restaurants - Ajay has some and find other online - find evaluation measures, ML algos used, features used | Research | 2 | All
8 | Code to find data overlap - yelp and govt data, and creating final dataset for us | Data preprocessing | 2
9 | Find feature importance (using Pearson coefficient or other) and check which features are more useful | Data analysis | 1
10 | Visualization of various features to test the spread of data - graph between features and graph between feature-health score | Data analysis | 1
11 | Find statistics of Grade vs number of restaurants | Data analysis | 1
12 | Find statistics of health score vs number of restaurants | Data analysis | 1
13 | Find statistics of region vs number of restaurants | Data analysis | 1