## October
S.No | Tasks | Type of task | No of people required | Person | Progress | Completion Date
1 | Exploring yelp dataset - find which all features, regions exist | Data exploration | 2 |  | Done | 2018-10-06
2 | Isolate data according to states and Las Vegas from yelp data - coding | Data preparation | 1 | Devershi | Working
3 | For Las Vegas yelp data, Find how much missing data exist - which restaurants have all data missing, some data missing | Data preparation | 1 | Devershi | Working |  | Find missing columns for each business_id. Eg business_id : 3,[column1, column2, column3]
4 | Yelp business json processing | Data preparation | 1 | Rimsha | Working
5 | Government data preparation | Data preparation |  | Rajdeep | Working
6 | Crawling to get inspection/voilations |  |  | Rajdeep and Ajay |  | 2018-10-11 | Postponed this task. Not required for now
7 | Based on task 1, Pick up regions and find government provided data availability online, if they have health score, format of data (csv, excel, to be scraped?) | Data collection | 2 |  | Done | 2018-10-06
8 | Study existing papers on finding health score for restaurants - Ajay has some and find other online - find evaluation measures, ML algos used, features used | Research |  | All
9 | Code to find data overlap - yelp and govt data, and creating final dataset for us | Data preparation | 1 | Ajay | Working
10 | Scrap data from Yelp website - by checking restaurant name, city, zip | Data Collection | 1 | Ajay | Working
11 | Merge scraped data from Yelp with final dataset | Data preparation |  | Ajay
12 | Find feature importance (using Pearson coefficient or other) and check which features are more useful - may require reading literature | Data analysis | 1 | Rajdeep and Rimsha
13 | Visualization of various features to test the spread of data - graph between features and graph between feature-health score | Data analysis | 1 | Devershi
14 | Python script to find statistics and plot graph of Grade vs number of restaurants - Useful to find how many restaurant have grade A, how many have B, C, D, … | Data analysis | 1 | Rajdeep
15 | Python script to find statistics and plot graph of health score vs number of restaurants - Useful to find how many restaurants have Health Score between 90-100, how many have score between 80-90, … | Data analysis | 1 | Rimsha
16 | Python script to find statistics of region vs number of restaurants | Data analysis | 1 | Devershi | Working | 2018-10-11 | Added state wise count
17 | Find best metric for similarity matching and Python script to implement it | Data mining | 1 | Devershi!!!???
18 | Python script for model based/ user based matching and fill data | Data mining | 1
19 | Python script to find mean score of restaurant for each zip code - Useful to show which regions perform good and which perform bad generally | Data analysis | 1
20 | Python script to plot graph between feature values (x-axis) vs health score (y-axis) - for each feature to be used in training - For e.g It is useful to determine what is the mean score of restaurant with rating 1, what is mean score of restaurant with rating 2, 3, 4, 5 | Data analysis | 2
21 | Python script to divide dataset into training, validation, and test set | Machine Learning | 1
22 | Python script to save and load the model - Useful for future | Machine Learning | 1
23 | Python script to determine TP, TN, FP, FN, Sensitivity (recall), Specificity, precision, F1 score, Accuracy | Machine Learning | 1
24 | Python script to plot ROC and AUC | Machine Learning | 1